## Cover Page
Courier Tracking System
Sprint Backlog
|  | Prepared by/ Updated by | Reviewed By | Approved By
| Name | Anshul Bais, Ankitha V, Shreyashree Ravutla, Raaghul Velumani, Yasaschandra Nagasai Kasaraneni
Role
Signature
| Date | 24/01/2022
:
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Sprint Backlog - Instructions C3: Protected Controlled Copy
Sprint Backlog
The Sprint Backlog is the set of Product Backlog items selected for the Sprint, plus a plan for delivering the product Increment and realizing the Sprint Goal. The Sprint Backlog is a forecast by the Development Team about what functionality will be in the next Increment and the work needed to deliver that functionality into a “Done” Increment.The Sprint Backlog is the output of the sprint planning meeting. It is essentially the list of tasks that the Scrum team needs to complete during the sprint in order to turn a selected set of product backlog items into a deliverable increment of functionality.
Sample
The sheet sample is an example sheet on how to fill the sprint backlog. Trainees can refer it to fill the details in the sheets Sprint 1/2/3.
Sprint 1/2/3
| User Story & Task Id | List the User Story id taken from product backlog that are selected to be completed in the particular sprint & List the number of tasks the User story is split into..
| Task | Name the tasks the user story is split into.
| Story Points | Enter the story points that was given for the user story during Sprint planning
| Assigned to | Name the person responsible for the particular task
| Status | Status of the Task - In progress/Completed
| Original Estimate | Original estimate of the task
| Day 1/2/3/4/5 | Task done in Day1/2/3/4/5 - Sprint review and retrospective to be held on Day 5
| Total | Summation of the estimation per day. To be filled with the total of the estimations filled.
| Charts | Chart is self driven as per the task burned

## Sprint -1
Sprint Backlog Courier Tracking System Project ID: A036 C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
US_1 | Initial Selection | 3
Task_1 | Design code for login/registration page |  | Raaghul Velumani | Completed | 1 | 1 | 0 | 0 | 0 | 0
Task_2 | Develop code for login/registartion page |  | Raaghul Velumani | Completed | 1 | 1 | 0 | 0 | 0 | 0
US_2 | User/staff/admin Registration | 5
Task_1 | Design form for registration |  | Shreyasree Ravutla | Completed | 1 | 1 | 0 | 0 | 0 | 0
Task_2 | Validate the data in form |  | Shreyasree Ravutla | Completed | 1 | 1 | 0 | 0 | 0 | 0
Task_3 | Insert the valid data in to the database table |  | Raaghul Velumani | Completed | 2 | 1 | 1 | 0 | 0 | 0
Task_4 | Displaying error message |  | Raaghul Velumani | Completed | 1 | 0 | 1 | 0 | 0 | 0
US_3 | User/staff/admin Authentication | 3
Task_1 | Create the form |  | Ankitha V | Completed | 1 | 1 | 0 | 0 | 0 | 0
Task_2 | Retriving the details from database |  | Ankitha V | Completed | 2 | 1 | 1 | 0 | 0 | 0
Task_3 | Authenticate login details |  | Raaghul Velumani | Completed | 2 | 1 | 1 |  | 0 | 0
Task_4 | Display home page, if valid |  | Ankitha V | Completed | 1 | 0 | 1 | 0 | 0 | 0
US_4 | View Registration request approvals | 5
Task_1 | Retrive the approvals from database |  | Anshul Bais | Completed | 3 | 1 | 2 | 0 | 0 | 0
Task_2 | Design the form |  | Raaghul Velumani | Completed | 1 | 0 | 1 | 0 | 0 | 0
US_5 | Staff Registration approval | 8
Task_1 | Approve registration request |  | Anshul Bais | Completed | 2 | 1.5 | 0.5 |  | 0 | 0
Task_2 | Change the request status in database |  | Anshul Bais | Completed | 1 | 1 | 0 | 0 | 0 | 0
Task_3 | Display login page or display error message |  | Raaghul Velumani | Completed | 1 | 1 | 1 | 0 | 0 | 0
US_6 | Admin registration approval | 3
Task_1 | Design the form |  | Raaghul Velumani | Completed | 1 | 0.5 | 0.5 | 0.5 | 0 | 0
Task_2 | Approve the reqistration request |  | Raaghul Velumani | Completed | 2 | 0.5 | 0.5 | 1.5 | 0 | 0
Task_3 | Display the login page, if successful |  | Yasaschandranagsai Kasaraneni | Completed | 1 | 0 | 1 | 0 | 0 | 0
US_7 | Warehouse Update | 8
Task_1 | Design the form |  | Raaghul Velumani | Completed | 1 | 1 | 1 | 1 | 1 | 0
Task_2 | Getting details from the user |  | Anshul Bais | Completed | 2 | 0.5 | 0.5 | 1 | 1 | 1
Task_3 | Validate details entered in the form |  | Anshul Bais | Completed | 3 | 1 | 1 | 1 | 2 | 0
Task_4 | Insert into database |  | Shreyasree Ravutla | Completed | 1 | 0.5 | 0.5 | 1 | 0 | 0
Task_5 | Display error message, if invalid |  | Anshul Bais | Completed | 2 | 1 | 0 | 1.5 | 1 | 0
US_8 | Update Quote | 5
Task_1 | Design the page |  | Yasaschandranagsai Kasaraneni | Completed | 2 | 1 | 0.5 | 0.5 | 1 | 0
Task_2 | Retrieve the data given by admin |  | Yasaschandranagsai Kasaraneni | Completed | 3 | 1 | 2 | 1 | 0 | 1
Task_3 | Update database, if valid |  | Raaghul Velumani | Completed | 1 | 0.5 | 1 | 1 | 0 | 0.5
US_9 | Update Parcel Types | 3
Task_1 | Design webpage |  | Yasaschandranagsai Kasaraneni | Completed | 1 | 0.5 | 0.5 | 1 | 0 | 0
Task_2 | Update database, if valid |  | Yasaschandranagsai Kasaraneni | Completed | 2 | 1 | 2 | 0 | 1 | 1
US_10 | Mapping Parcel Type | 3
Task_1 | Design the form |  | Anshul Bais | Completed | 1 | 1 | 0.5 | 0.5 | 1 | 0
Task_2 | Display quotes for parcel types |  | Yasaschandranagsai Kasaraneni | Completed | 2 | 1 | 2 | 1 | 1 | 0.5
Task_3 | Update quotes for parcel types |  | Yasaschandranagsai Kasaraneni | Completed | 2 | 0.5 | 0.5 | 1 | 1 | 0
US_11 | Update Offers | 1
Task_1 | Design the form |  | Ankitha V | Completed | 1 | 0.5 | 1 | 1 | 0.5 | 0
Task_2 | Enter the offers available |  | Ankitha V | Completed | 2 | 1 | 2 | 1 | 1.5 | 0.5
Task_3 | Update the offers in the database |  | Raaghul Velumani | Completed | 1 | 0.5 | 1 | 2 | 1 | 1
US_12 | View Offers | 1
Task_1 | Display the offers available for user |  | Shreyasree Ravutla | Completed | 3 | 1 | 2 | 2 | 1 | 0.5
US_13 | Update policy details | 3
Task_1 | Design the form |  | Anshul Bais | Completed | 1 | 0 | 0.5 | 1 | 1 | 0
Task_2 | Update policy details in database |  | Raaghul Velumani | Completed | 2 | 0 | 0.5 | 1.5 | 1 | 1
US_14 | View Policy | 3
Task_1 | Retrieve policy details from database |  | Shreyasree Ravutla | Completed | 2 | 0.5 | 1.5 | 1 | 3 | 1
Task_2 | Display policy details |  | Yasaschandranagsai Kasaraneni | Completed | 1 | 0.5 | 1 | 0.5 | 1 | 1
US_15 | View/Modify staff | 5
Task_1 | Display the webpage for admin |  | Ankitha V | Completed | 1 | 0.5 | 0.5 | 1 | 2 | 1
Task_2 | Retrieve the details of staff according to id selected |  | Raaghul Velumani | Completed | 4 | 1 | 1 | 3 | 1 | 0.5
Task_3 | Update the details of staff |  | Anshul Bais | Completed | 2 | 0.5 | 0.5 | 2 | 1 | 0
US_16 | Consignment Details | 5
Task_1 | Design the form |  | Shreyasree Ravutla | Completed | 1 | 0 | 0.5 | 0.5 | 2 | 1
Task_2 | Getting details from the user |  | Ankitha V | Completed | 3 | 2 | 1 | 2 | 1 | 1
Task_3 | Update the database |  | Yasaschandranagsai Kasaraneni | Completed | 2 | 0.5 | 0.5 | 1 | 2 | 1
US_17 | Consignment Receipt | 3
Task_1 | Design the form |  | Anshul Bais | Completed | 1 | 1 | 2 | 1 | 1 | 1
Task_2 | Getting details and calculating amount |  | Shreyasree Ravutla | Completed | 3 | 1 | 0.5 | 2 | 1 | 3
Task_3 | Generate bill and redirect to payment process |  | Raaghul Velumani | Completed | 1 | 0.5 | 1 | 2 | 3 | 1
US_18 | Bill Generation | 3
Task_1 | Generate bill according to the date |  | Yasaschandranagsai Kasaraneni | Completed | 2 | 1 | 1 | 2 | 0.5 | 1
Task_2 | Display the bill details |  | Ankitha V | Completed | 1 | 0.5 | 1 | 1 | 0 | 2
US_19 | Quotation request | 5
Task_1 | Design the form |  | Anshul Bais | Completed | 1 | 0 | 1 | 3 | 1 | 0.5
Task_2 | Retrieve details from the database |  | Raaghul Velumani | Completed | 2 | 1 | 0.5 | 2.5 | 1 | 2
Task_3 | Display the data |  | Shreyasree Ravutla | Completed | 1 | 0.5 | 1 | 1 | 2 | 1
US_20 | Profile update/view | 3
Task_1 | Design the webpage |  | Shreyasree Ravutla | Completed | 1 | 0 | 0.5 | 1 | 1 | 0.5
Task_2 | Display the details of user |  | Yasaschandranagsai Kasaraneni | Completed | 2 | 1 | 1 | 3 | 1 | 2
Task_3 | Update the details |  | Yasaschandranagsai Kasaraneni | Completed | 1 | 1.5 | 1 | 2.5 | 2 | 3
Task_4 | Display the success message |  | Shreyasree Ravutla | Completed | 1 | 1 | 2 | 0.5 | 3 | 1
TOTAL |  |  |  |  | 91 | 41.5 | 49.5 | 54.5 | 45.5 | 31.5

## Sprint -2
Sprint Backlog Courier Tracking System Project ID: A036 C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
US_21 | Package Registration | 5
Task_1 | Forward to registration package form |  | Anshul Bais | Completed | 2 | 2 | 1 | 0 | 0 | 0
Task_2 | Design the form for entering details |  | Raaghul Velumani | Completed | 1 | 0.5 | 0.5 | 0 | 0 | 0
Task_3 | Validate the data entered in form |  | Shreyashree Ravutla | Completed | 3 | 2 | 1 | 0 | 0 | 0
Task_4 | Insert data into database |  | Ankitha V | Completed | 2 | 1.5 | 1 | 0 | 1 | 0
US_22 | Package location update | 3
Task_1 | Design the page and getting details from user |  | Yasaschandranagasai kasaraneni | Completed | 2 | 1 | 1 | 1 | 0 | 0
Task_2 | Validate the input given by user |  | Raaghul Velumani | Completed | 1 | 0.5 | 0.5 | 0 | 0 | 0
Task_3 | Update the database and redirecting to next page |  | Shreyashree Ravutla | Completed | 2 | 0.5 | 1 | 1 | 0 | 0
US_23 | Package Tracking | 8
Task_1 | Design the track package web page |  | Anshul Bais | Completed | 1 | 0.5 | 0.5 | 0.5 | 0 | 0
Task_2 | Enter the package id and validate the data |  | Yasaschandranagasai kasaraneni | Completed | 3 | 2 | 2 | 1 | 0 | 0
Task_3 | Retrieve the details of package from database |  | Yasaschandranagasai kasaraneni | Completed | 2 | 1 | 1 | 0.5 | 0 | 0
Task_4 | Display the package status |  | Ankitha V | Completed | 1 | 1 | 0.5 | 1 | 0 | 0
US_24 | Package Delivery update | 3
Task_1 | Design the web page |  | Shreyashree Ravutla | Completed | 1 | 0.5 | 0.5 | 1 | 0 | 0
Task_2 | Update the delivery status in database |  | Ankitha V | Completed | 2 | 0 | 1 | 1 | 1 | 0
US_25 | Package Delivery | 5
Task_1 | Retrieve the status of delivery from database |  | Anshul Bais | Completed | 2 | 0.5 | 1 | 1 | 0.5 | 0
Task_2 | Display the status of delivery |  | Raaghul Velumani | Completed | 1 | 0.5 | 0.5 | 1 | 0 | 0.5
US_26 | Package Delivery status | 3
Task_1 | Design the web page |  | Shreyashree Ravutla | Completed | 1 | 0 | 0.5 | 0.5 | 1 | 0
Task_2 | Retrieve the status from database |  | Yasaschandranagasai kasaraneni | Completed | 3 | 1 | 2 | 0.5 | 0.5 | 1
Task_3 | Display status to user |  | Raaghul Velumani | Completed | 2 | 1 | 0.5 | 0.5 | 1 | 0
US_27 | Warehouse update | 3
Task_1 | Design the webpage for getting details |  | Anshul Bais | Completed | 1 | 1 | 1 | 0.5 | 1 | 1
Task_2 | Validate the data entered in form |  | Shreyashree Ravutla | Completed | 3 | 3 | 2 | 1 | 2 | 1
Task_3 | Update the data in database |  | Raaghul Velumani | Completed | 2 | 2 | 1 | 1 | 1 | 0
US_28 | Country/State update | 5
Task_1 | Design the form for getting details of country |  | Ankitha V | Completed | 1 | 1 | 0.5 | 1 | 2 | 1
Task_2 | Verify the entered country with zip code |  | Yasaschandranagasai kasaraneni | Completed | 4 | 1 | 2 | 0.5 | 1 | 3
Task_3 | Update the database, if valid |  | Raaghul Velumani | Completed | 2 | 0.5 | 1 | 1 | 0.5 | 1
US_29 | View Registration details | 3
Task_1 | Design the web page and retrieve details |  | Anshul Bais | Completed | 1 | 1 | 1 | 0.5 | 2 | 1
Task_2 | Display the details to user |  | Shreyashree Ravutla | Completed | 4 | 1 | 1 | 2 | 0.5 | 0.5
US_30 | Parcel Request | 3
Task_1 | Design webpage |  | Ankitha V | Completed | 1 | 1.5 | 1 | 1 | 0.5 | 1
Task_2 | Retrieve request details and display details |  | Yasaschandranagasai kasaraneni | Completed | 3 | 1 | 2 | 1 | 0.5 | 1
US_31 | Generate reports | 3
Task_1 | Design webpage for generating report |  | Anshul Bais | Completed | 2 | 1 | 0.5 | 1 | 1 | 1
Task_2 | Retrieve data according to option selected |  | Raaghul Velumani | Completed | 4 | 1 | 1 | 2 | 1.5 | 2.5
Task_3 | Display the report generated |  | Shreyashree Ravutla | Completed | 3 | 1 | 1 | 0.5 | 1 | 2
US_32 | Help | 3
Task_1 | Display page for displaying available help options |  | Yasaschandranagasai kasaraneni | Completed | 2 | 0.5 | 0.5 | 1.5 | 2 | 1
Task_2 | Display page to get the issues faced by user |  | Raaghul Velumani | Completed | 4 | 1 | 0.5 | 2 | 1 | 2
Task_3 | Update database |  | Ankitha V | Completed | 3 | 0 | 1 | 0.5 | 1 | 0.5
US_33 | Password recovery | 3
Task_1 | Display secret questions and save answers in database |  | Shreyashree Ravutla | Completed | 3 | 0.5 | 0.5 | 1 | 1 | 2
Task_2 | Validate and if id is required id is shown |  | Anshul Bais | Completed | 2 | 1 | 1.5 | 0.5 | 2 | 1
Task_3 | Validate and if password is required the user resets it |  | Yasaschandranagasai kasaraneni | Completed | 1 | 0.5 | 1 | 1 | 0.5 | 0.5
Task_4 | Update the database |  | Raaghul Velumani | Completed | 2 | 1 | 2 | 2.5 | 1 | 1
US_34 | Reviews | 1
Task_1 | Design webpage for getting answers for quessionnaire |  | Anshul Bais | Completed | 3 | 0 | 1 | 0.5 | 2 | 1.5
US_35 | Review Questionnaire | 3
Task_1 | Design webpage for questionnaire and answers |  | Ankitha V | Completed | 3 | 2 | 0.5 | 1 | 2 | 1
Task_2 | Update data in the database |  | Raaghul Velumani | Completed | 2 | 1 | 1 | 1 | 1 | 2
US_36 | Trigger Review | 1
Task_1 | Design the webpage to display message |  | Shreyashree Ravutla | Completed | 2 | 2 | 0.5 | 1 | 1.5 | 2
Task_2 | Direct to review page irrespective of delivery status |  | Yasaschandranagasai kasaraneni | Completed | 3 | 1 | 1 | 0.5 | 2 | 1
US_37 | Customer/Admin logoff | 1
Task_1 | Save the changes made in the database |  | Raaghul Velumani | Completed | 2 | 1 | 1 | 1.5 | 2 | 1
Task_2 | Redirect to home page |  | Anshul Bais | Completed | 1 | 2.5 | 1 | 2 | 0.5 | 2.5
TOTAL |  |  |  |  | 96 | 46 | 44 | 40 | 39 | 36.5

## Data (hidden)
In-Progress
Completed
N/A